ATLAS

Implementation Plan

AppLogica Desk

Enterprise IT Service Management Platform

| Document ID | ATLAS-IMPL-DESK-v1.0 |
| --- | --- |
| Product Code | ATLAS-ITSM |
| External Name | AppLogica Desk |
| Wave | Wave 3 - Enterprise Products |
| Timeline | Week 15-20 (6 weeks to Beta) |
| ITIL Standard | ITIL v4 |
| OSS Reference | iTop, GLPI (domain reference only) |
| Tech Stack | .NET 8 + React 18 + PostgreSQL + Flutter |
| Target Regions | Egypt, KSA, UAE, International |
| Version | v1.0 - March 01, 2026 |

# 1. Product Overview

## 1.1 Product Vision

AppLogica Desk is an enterprise-grade IT Service Management platform built to ITIL v4 standards. It provides organizations in the MENA region with a unified ITSM solution covering the full spectrum of IT operations: Incident Management, Service Request fulfillment, Problem Management, Change Enablement, and lightweight Configuration Management.

Unlike AppLogica Resolve (which targets external customer support), Desk is purpose-built for internal IT organizations — providing IT help desks, service delivery teams, and IT operations with the tooling, governance, and AI augmentation required to manage complex enterprise IT environments.

## 1.2 Strategic Rationale

- Internal Demand: Every enterprise ATLAS customer requires ITSM tooling for their internal IT operations

- Ecosystem Fit: Desk complements Resolve (external support), Connect (omnichannel intake), and Nexus (ERP/asset data)

- ITIL v4 Compliance: MENA enterprises increasingly require formal ITSM frameworks for regulatory and audit purposes

- AI Differentiation: Smart classification, RAG-powered KB, anomaly detection, and copilot guidance are key competitive advantages

- Wave 3 Synergy: Co-delivered with Pulse (CRM) and Nexus (ERP) to enable cross-product data flows for asset, procurement, and customer impact analysis

## 1.3 Core Modules

| Module | Description | Priority |
| --- | --- | --- |
| Incident Management | Full ITIL lifecycle: triage, assignment, escalation, Major Incident mode | P0 - Critical |
| Service Request Management | Service catalog, dynamic forms, multi-stage approval workflows | P0 - Critical |
| SLA & Governance | Multi-policy SLA engine, business hours, breach prediction, OLA tracking | P0 - Critical |
| Agent Workspace | Unified inbox, real-time updates, bulk actions, on-call scheduling | P0 - Critical |
| Knowledge Management | Article versioning, AI-assisted authoring, RAG-powered search | P1 - High |
| Problem Management | RCA workspace, KEDB, incident linking, trend detection | P1 - High |
| Change Management | RFC workflow, CAB, change calendar, conflict detection | P1 - High |
| CMDB (Lightweight) | CI registry, relationship mapping, impact analysis | P1 - High |
| Reporting & Analytics | ITIL KPIs, AI narratives, custom dashboards, scheduled reports | P1 - High |
| AI Layer | Copilot, classification, RAG, task automation, anomaly detection | P1 - High |
| Mobile Agent App | Flutter iOS/Android app for core incident and request management | P2 - Medium |

## 1.4 Relationship to AppLogica Resolve

AppLogica Desk and AppLogica Resolve are complementary products with distinct audiences and workflows. Both consume ATLAS shared platform services and publish/consume events via the ATLAS Event Bus.

| Dimension | AppLogica Resolve | AppLogica Desk |
| --- | --- | --- |
| Audience | External customers | Internal IT teams |
| Standard | Customer support best practices | ITIL v4 |
| Key Processes | Ticket lifecycle, SLA, CSAT | Incident, Request, Problem, Change |
| CMDB | None | Lightweight CI registry |
| CAB/Change Calendar | None | Full Change Enablement |
| Problem Management | None | Full ITIL Problem practice |
| Event Bus | Publishes: ticket.created, ticket.resolved | Publishes: incident.*, change.*, desk.sla.* |
| Cross-product | Can receive desk.incident.created events | Can receive resolve.ticket events for impact view |

# 2. Technology & Architecture

## 2.1 Technology Stack

| Layer | Technology |
| --- | --- |
| Backend Framework | .NET 8 + Clean Architecture + MediatR + FluentValidation |
| Frontend | React 18 + TypeScript + Ant Design + i18next |
| Mobile | Flutter 3.x (iOS + Android — agent app) |
| Database | PostgreSQL 15 (schema-per-tenant isolation) |
| Cache & Pub/Sub | Redis 7 (SLA timers, real-time breach alerts, session) |
| Search | Elasticsearch 8 (full-text, RAG vector indexing) |
| Message Queue | RabbitMQ + MassTransit (event-driven integration) |
| Background Jobs | Hangfire (SLA engine, escalations, scheduled reports) |
| Real-time | SignalR (agent inbox live updates, SLA warnings) |
| Container | Docker + Kubernetes (AKS) |
| Cloud Platform | Azure (primary) — AKS, PostgreSQL Flexible, Azure Cache, Storage |
| AI Platform | ATLAS AI Gateway (Azure OpenAI / Anthropic Claude backend) |
| CI/CD | GitHub Actions + Azure Container Registry |
| Observability | OpenTelemetry + Azure Monitor + Application Insights |

## 2.2 OSS Reference Analysis

| OSS Project | Evaluation Purpose | Decision | Outcome |
| --- | --- | --- | --- |
| iTop | Full ITSM reference implementation and ITIL process mapping | Reference only | Domain knowledge extraction — not forked |
| GLPI | CMDB structure and CI type modeling reference | Reference only | CI schema patterns adopted |
| Zammad | Ticket domain model (already used by Resolve) | Reference only | Proven patterns via Resolve implementation |
| FreeScout | Agent workspace UX patterns | Reference only | UX research only |
| Mattermost | Internal collaboration patterns for Major Incident mode | Not used | MS Teams webhook integration preferred |

## 2.3 ATLAS Integration Points

| ATLAS Service | Integration | Dependency | Protocol |
| --- | --- | --- | --- |
| Identity Service | Agent/requester auth, RBAC roles, SSO, team sync | Critical | REST + JWT |
| Tenant Management | Tenant lifecycle, branding, config (SLA defaults, language) | Critical | REST + Event Bus |
| API Gateway | Rate limiting, request routing, token validation | Critical | HTTP Proxy |
| Event Bus (RabbitMQ) | Publish/consume all ITSM domain events | High | AMQP + MassTransit |
| AI Gateway | Copilot, classification, RAG, narrative generation | High | REST |
| Notify Service | Email, SMS, push, MS Teams notifications | High | REST + Events |
| File Storage | Ticket attachments, KB media, export artifacts | Medium | REST (Azure Blob) |
| AppLogica Resolve | Cross-system incident visibility (external vs internal) | Medium | Event Bus |
| AppLogica Connect | Incidents sourced from omnichannel interactions | Medium | Event Bus |
| AppLogica Nexus | Asset/CI sync, procurement request creation | Low | Event Bus |

## 2.4 Microservice Topology

AppLogica Desk deploys as three independent services within the tenant's Kubernetes namespace:

- desk-api — Main REST API serving all ITSM operations. Horizontally scalable. Exposed via ATLAS API Gateway.

- desk-worker — Hangfire background job host: SLA timer engine, escalation processor, KB indexer, report generator, AI classification consumer. No external ingress.

- desk-signalr — Dedicated SignalR hub for real-time agent inbox updates and SLA breach alerts. Requires sticky session routing.

# 3. Domain Model

## 3.1 Core Entities

| Entity | Key Attributes | Relationships |
| --- | --- | --- |
| Incident | TicketNumber, Title, Status, Priority, Impact, Urgency, Category, IsMajorIncident | Belongs to Queue, assigned to Agent, linked to CI, Problem, Change |
| SlaTimer | ResponseDueAt, ResolutionDueAt, Status, ElapsedPercent, PauseReason | Linked to Incident or ServiceRequest, governed by SlaPolicy |
| SlaPolicy | Name, Targets (Priority → ResponseMins/ResolutionMins), BusinessHoursCalendarId | Applied to Incidents and ServiceRequests |
| ServiceCatalogItem | Name, FormSchema (JSONB), ApprovalWorkflow, EstimatedFulfillmentHours | Has ServiceRequests, owned by Team |
| ServiceRequest | TicketNumber, Status, FormData (JSONB), CurrentApprovalStep | References ServiceCatalogItem, has ApprovalRecords and FulfillmentTasks |
| Problem | TicketNumber, Status, RootCauseSummary, IsKnownError, Workaround | Linked to Incidents, promoted to ChangeRequest |
| ChangeRequest | TicketNumber, ChangeType, RiskLevel, ScheduledStart, RollbackPlan, HasConflicts | Linked to CabMeeting, affectedCIs, linked Problem |
| CabMeeting | ScheduledAt, Agenda, Quorum, VotingDeadline | Has ChangeRequests, CAB Members (Agents) |
| ConfigurationItem | Name, CiType, Status, Attributes (JSONB) | Has CI Relationships, linked to Incidents and Changes |
| KnowledgeArticle | Title, Body, Status, Version, IsAiGenerated, Locale | In Category, tagged, linked to Incident (if AI-generated) |
| Agent | Name, Email, Teams, Queues, OnCallSchedule | Assigned Incidents and ServiceRequests |
| Queue | Name, Type (Incident/Request/Change), DefaultSlaPolicy | Has Agents, receives routed tickets |
| AuditRecord | EntityType, EntityId, Action, OldValue, NewValue, ActorId, OccurredAt | Append-only, immutable, indexed by EntityId |

## 3.2 Incident State Machine

| Transition | From State | To State → Domain Event |
| --- | --- | --- |
| Create | (new) | New → desk.incident.created |
| Assign | New | Assigned → desk.incident.assigned |
| Start Work | Assigned | In Progress → desk.incident.in_progress |
| Suspend (customer wait) | In Progress / Assigned | Pending → desk.sla.paused |
| Escalate (tier) | Any active | Escalated → desk.incident.escalated |
| Declare Major | Any P0/P1 | Major → desk.incident.major_declared |
| Resolve | In Progress / Escalated / Major | Resolved → desk.incident.resolved |
| Close | Resolved | Closed → desk.incident.closed |
| Reopen | Resolved / Closed | Assigned → desk.incident.reopened |

# 4. Implementation Phases

## 4.1 Week 15–16: Foundation & Incident Core

| Task | Deliverable | Owner |
| --- | --- | --- |
| Solution Architecture | ADRs, API contracts, service topology, DB ERD | Solution Architect |
| Database Schema | Core DDL — Incidents, Queues, Agents, SlaPolicy, AuditLog | Database Architect |
| Backend Scaffold | .NET solution structure, Clean Architecture layers, shared kernel | Backend Architect |
| Incident Domain | Incident aggregate, state machine, domain events, repository interface | Backend Developer |
| Incident API | CRUD endpoints, state transitions, timeline, bulk operations | Backend Developer |
| ATLAS Identity Integration | JWT validation, RBAC middleware, agent profile sync | Backend Developer |
| Tenant Integration | Tenant config loading, branding, SLA defaults | Backend Developer |
| Frontend Scaffold | React app, routing, Ant Design theme, i18next setup, RTL config | Frontend Architect |
| Agent Inbox UI (skeleton) | Ticket list layout, filter panel, column configuration | Frontend Developer |
| SignalR Hub | Real-time update hub for agent inbox | Backend Developer |

Exit Criteria: Incident CRUD working end-to-end with ATLAS Identity integration. Agent inbox renders live data.

## 4.2 Week 16–17: SLA Engine & Agent Workspace

| Task | Deliverable | Owner |
| --- | --- | --- |
| SLA Policy Engine | Policy configuration, target calculation, business hours calendar | Backend Developer |
| SLA Timer Service | Response/resolution timer, pause/resume, breach tracking | Backend Developer |
| Breach Prediction | Warning threshold logic, desk.sla.warning event publisher | Backend Developer |
| Hangfire Jobs | SLA timer evaluation job (60-second cycle), escalation processor | Backend Developer |
| Notify Integration | SLA breach alerts via Notify Service (email + push) | Backend Developer |
| Agent Inbox (full) | Filters, saved views, bulk actions, keyboard shortcuts, SLA risk indicators | Frontend Developer |
| Ticket Detail View | Timeline, inline comments, @mentions, action panel | Frontend Developer |
| SLA Status Widget | Real-time SLA countdown, warning/breach visual states | Frontend Developer |
| RTL & i18n | Full Arabic localization, RTL layout validation for all components | Frontend Developer |

Exit Criteria: SLA engine tracking incidents accurately. Breach notifications firing. Agent inbox feature-complete.

## 4.3 Week 17–18: Service Catalog & Problem Management

| Task | Deliverable | Owner |
| --- | --- | --- |
| Service Catalog API | Catalog item CRUD, category management, dynamic form schema | Backend Developer |
| Approval Workflow Engine | Sequential/parallel approval chains, delegation, timeout escalation | Backend Developer |
| Fulfillment Task Tracking | Task checklist per request, completion tracking | Backend Developer |
| Service Request API | Submit, approve, reject, cancel endpoints | Backend Developer |
| Service Catalog UI | End-user catalog browser, dynamic form renderer | Frontend Developer |
| Request Approval UI | Approver dashboard, one-click approve/reject, delegation | Frontend Developer |
| Requester Self-Service Portal | Request submission, status tracking, history | Frontend Developer |
| Problem Management API | Problem CRUD, incident linking, KEDB promotion | Backend Developer |
| Problem Workspace UI | RCA workspace, 5-Why template, incident link manager | Frontend Developer |
| Trend Detection (AI) | Recurring incident pattern detection via AI Gateway | Backend Developer |

Exit Criteria: Service catalog requests submittable end-to-end with approvals. Problem records linked to incidents.

## 4.4 Week 18–19: Change Management & CMDB

| Task | Deliverable | Owner |
| --- | --- | --- |
| Change Request API | RFC create, CAB submit, vote, implement, PIR endpoints | Backend Developer |
| CAB Meeting Engine | Meeting scheduling, agenda, quorum voting, digital approval | Backend Developer |
| Change Calendar API | Date range query, conflict detection algorithm | Backend Developer |
| Conflict Detection | Overlapping CI + time window detection | Backend Developer |
| CMDB API | CI CRUD, relationship management, impact analysis (recursive CTE) | Backend Developer |
| CMDB Auto-sync Webhooks | Azure Monitor and generic webhook receiver for CI updates | Backend Developer |
| Change Calendar UI | Visual calendar, color-coding, drag-to-reschedule, conflict indicators | Frontend Developer |
| RFC Form UI | Dynamic RFC form, risk assessment wizard, CI selector | Frontend Developer |
| CMDB UI | CI list/detail, relationship graph visualization, impact display | Frontend Developer |
| Admin Configuration UI | SLA policies, business hours, queues, teams, service catalog admin | Frontend Developer |

Exit Criteria: Full Change Management workflow (Draft → CAB → Approve → Implement). CMDB CIs registered and linked to incidents.

## 4.5 Week 19–20: AI Layer, KB, Reporting & Beta

| Task | Deliverable | Owner |
| --- | --- | --- |
| Knowledge Base API | Article CRUD, versioning, category taxonomy, full-text search | Backend Developer |
| KB Elasticsearch Index | Index schema, sync consumer via MassTransit | Backend Developer |
| AI Copilot Integration | System prompt configuration, context enrichment, ATLAS AI Gateway proxy | AI/ML Engineer |
| AI Classification Pipeline | Incident auto-classification on creation, confidence thresholds | AI/ML Engineer |
| RAG KB Suggestions | Vector indexing, hybrid retrieval, article suggestion during intake | AI/ML Engineer |
| AI KB Article Generation | Auto-draft from resolved incident notes, mandatory review gate | AI/ML Engineer |
| Anomaly Detection | Incident spike detection, NL narrative generation, dashboard cards | AI/ML Engineer |
| SLA Dashboard | Real-time SLA compliance chart, MTTR/MTTD, breach heatmap | Frontend Developer |
| Reporting Engine | Pre-built reports, export (PDF/Excel), scheduled delivery | Backend Developer |
| Mobile Agent App (Flutter) | Core screens: inbox, ticket detail, assign, resolve, comment | Mobile Developer |
| Integration Testing | End-to-end test suites across all modules | QA Engineer |
| Security Testing | OWASP scan, tenant isolation pen test, RLS validation | AppSec Engineer |
| Performance Testing | Load test: 500 concurrent agents, 100k active SLA timers | QA Engineer |
| Arabic Localization Final | Complete translation review, RTL validation, PDF Arabic export | Frontend Developer |

Exit Criteria: All modules Beta-complete. AI features integrated. Security scan passed. Performance targets met.

# 5. AI Integration

## 5.1 AI Capabilities Overview

| AI Capability | Implementation | ATLAS AI Gateway Endpoint | Human Gate |
| --- | --- | --- | --- |
| ITSM Copilot | Contextual Q&A for agents — KB, ITIL guidance, workflow help | /v1/chat | Advisory only — no autonomous actions |
| Incident Classification | Auto-classify category, priority, CI, recommended queue on creation | /v1/actions | Manual if confidence < 70% |
| KB Article Suggestions | RAG retrieval of articles during incident intake | /v1/rag | None — display only |
| KB Article Generation | Draft article from resolved incident notes | /v1/actions | Mandatory review before publish |
| Anomaly Detection | Incident spike detection, pattern clustering, SLA risk signals | /v1/actions (scheduled) | Dashboard display with human decision |
| NL Report Narratives | Plain-language explanation of KPI dashboards and anomalies | /v1/chat | Clearly labeled as AI-generated |

## 5.2 AI Governance Rules

- All LLM requests routed exclusively through ATLAS AI Gateway — no direct API calls to Azure OpenAI or Anthropic

- AI-generated content displayed with visible 'AI Draft - Review Required' label in UI

- No AI action modifies system state without human confirmation (classification auto-apply above 70% threshold is the only exception, and is fully logged)

- All AI interactions — prompts, completions, confidence scores, applied vs suggested — written to immutable audit log

- Fallback behavior defined for all AI features: graceful degradation when AI Gateway is unavailable

- Arabic-language inputs processed natively — no transliteration or forced translation before classification

## 5.3 RAG Pipeline Architecture

Knowledge retrieval uses a hybrid approach combining BM25 keyword search (Elasticsearch) with dense vector similarity (ATLAS AI Gateway embedding endpoint). Candidates are reranked before presentation.

| Stage | Implementation |
| --- | --- |
| Indexing | Article → chunked (512 tokens, 50 overlap) → embedded via AI Gateway → stored in per-tenant vector index |
| Retrieval | Hybrid: BM25 top-20 + vector top-20 → deduplicated → top-20 merged candidates |
| Reranking | Cross-encoder reranking via AI Gateway → top-5 selected for response |
| Context Assembly | Top-5 chunks + metadata assembled into LLM prompt (max 4,000 tokens) |
| Freshness | Articles older than 180 days flagged with staleness indicator in results |
| Tenant Isolation | Separate vector namespace per tenant — no cross-tenant retrieval possible |
| Performance SLA | End-to-end retrieval target: < 300ms P95 |

# 6. Compliance & Regional Considerations

## 6.1 Data Residency & Privacy

| Region | Compliance Standard | Implementation |
| --- | --- | --- |
| Egypt | Egypt PDPL (Personal Data Protection Law) | Data stored in Egypt or EU West region. Consent tracking. Right-to-erasure workflow. |
| Saudi Arabia (KSA) | Saudi PDPL + SAMA requirements | Data stored in Azure KSA region. Data transfer restrictions enforced via tenant routing. |
| UAE | DIFC / ADGM data protection frameworks | Azure UAE North. Contractual data processing agreements. |
| International | GDPR | Azure West Europe. Full GDPR consent, retention, and subject request workflows. |

## 6.2 Arabic & RTL Requirements

- Full UI Arabic translation using i18next with RTL layout via CSS logical properties

- All exported PDFs (reports, ticket closures, SLA summaries) support Arabic bidirectional text

- Date and time formats localized: Hijri calendar display option for KSA tenants

- MENA business hours calendars: Friday-Saturday weekend for GCC tenants, Friday-only for Egypt

- All AI-generated content (KB articles, narratives, copilot) responds in Arabic when Arabic locale active

## 6.3 Audit & Compliance Logging

All state transitions, data modifications, and AI interactions are written to an append-only AuditRecord table. The audit log is immutable (enforced via PostgreSQL Row-Level Security policy preventing UPDATE/DELETE). Audit records include actor identity, timestamp, old and new values, and AI action flags. Logs are retained per tenant data retention policy and exportable in structured format for regulatory review.

# 7. Risks & Mitigations

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| SLA engine edge cases (timezone crossing, DST transitions, holiday boundary) | High — SLA accuracy failures erode trust | High | Comprehensive test suite with 25+ edge case tests using Testcontainers. Business hours calendar validated against real MENA public holiday data. |
| CMDB impact analysis performance at scale | Medium — slow impact queries block incident triage | Medium | PostgreSQL recursive CTE with depth limit (max 5). Indexed on CI type and tenant. Benchmark target: < 500ms for 500-node graphs. |
| Change calendar conflict detection accuracy | High — missed conflicts cause production incidents | Low | Conflict detection runs server-side on every scheduling mutation. CAB approval UI shows conflict warnings prominently. |
| AI classification false positives | Medium — incorrect auto-routing increases agent workload | Medium | 70% confidence threshold for auto-apply. All auto-applied classifications surfaced in audit log. Accuracy monitored per tenant with weekly review. |
| SignalR scaling under peak load | Medium — stale inbox frustrates agents during major incidents | Medium | Redis backplane for SignalR across multiple pods. Sticky sessions via Azure Application Gateway. Load tested at 500 concurrent agents. |
| Tenant data isolation failure in shared PostgreSQL schemas | Critical — regulatory and trust violation | Low | Schema-per-tenant enforced at EF Core level. TenantId filter on every repository query. Automated isolation tests in CI pipeline. |
| Wave 3 delivery timeline pressure (co-delivery with Pulse and Nexus) | Medium — feature scope may slip | Medium | P2 features (Full CMDB, Mobile App) scoped to post-Beta. CMDB limited to manual CI entry at Beta. Mobile app limited to Incident core. |
| Arabic OCR and RTL in exported PDFs | Low — cosmetic but visible to customers | Medium | PDF generation tested with Arabic content from day 1 using agreed PDF library supporting BiDi text. |

# 8. AI Prompts — Selected Examples

Full prompt library available in ATLAS-DESK-PROMPTS-v1.0 document. Selected examples below.

## 8.1 SLA Engine Design Prompt (D-ARCH-02)

[ROLE] Backend Architect specializing in SLA management and timer design.
[CONTEXT] Product: AppLogica Desk — SLA Engine. Tech: .NET 8, PostgreSQL, Redis, Hangfire.
Requirements: Multiple SLA policies per tenant, business hours, pause/resume, breach prediction.
[TASK] Design the complete SLA Engine for AppLogica Desk.
[CONSTRAINTS] SLA calculation must NEVER be inline in API handlers. All timer state in PostgreSQL for durability.
[OUTPUT FORMAT] ## SLA Engine Architecture ### Domain Model ### State Machine ### Calculation Algorithm ### Breach Prediction ### Background Jobs

## 8.2 Incident Classification Prompt (D-AI-02)

[ROLE] AI/ML Engineer designing automated ticket classification.
[CONTEXT] Input: Raw incident title + description (Arabic or English). Required outputs: Category, Subcategory, Priority (with confidence), Affected CI, Recommended Queue.
[TASK] Design the classification pipeline including prompt, confidence thresholds, and fallback.
[CONSTRAINTS] Confidence < 70% = suggestion only. Confidence >= 70% = auto-apply. All results logged to audit trail.
[OUTPUT FORMAT] ### Classification Prompt Template ### JSON Output Schema ### Confidence Threshold Logic

# 9. Quality Assurance & Beta Acceptance

## 9.1 Test Strategy

| Test Type | Coverage Target | Tool | Focus Areas |
| --- | --- | --- | --- |
| Unit Tests | > 85% | xUnit + Moq + FluentAssertions | SLA engine edge cases, state machine transitions, approval workflow logic |
| Integration Tests | All API endpoints | Testcontainers + PostgreSQL | Incident lifecycle, SLA lifecycle, approval workflows, CMDB impact |
| E2E Tests | All critical paths | Playwright | Incident intake to close, service request approval, change RFC to implementation |
| Performance Tests | Key endpoints | k6 | 500 concurrent agents, 100k SLA timers, inbox load < 1s P95 |
| Security Tests | OWASP Top 10 | OWASP ZAP + manual review | Tenant isolation, XSS, SQL injection, RBAC bypass attempts |
| Accessibility Tests | WCAG 2.1 AA | axe-core + manual review | Keyboard navigation, screen reader, color contrast, RTL |

## 9.2 Beta Acceptance Criteria

- Incident lifecycle fully operational: New → Assigned → In Progress → Resolved → Closed

- SLA engine accurately tracking response and resolution targets with breach notifications

- Service catalog: at least 3 catalog items with approval workflows functional end-to-end

- Change Management: RFC creation, CAB vote, and change calendar with conflict detection working

- Problem records linkable to incidents; KEDB promotion functional

- CMDB: CI registration, relationship creation, and basic impact analysis working

- Knowledge Base: article authoring, publishing, and RAG-based search functional

- AI copilot responding to ITSM questions in both English and Arabic

- SLA and incident volume reports exportable to PDF and Excel

- Arabic RTL UI fully validated across all primary screens

- No critical security findings from OWASP scan. Tenant isolation tests passing.

- Performance: inbox load < 1 second, SLA calculation < 100ms for single ticket

# 10. Document Cross-References

| Document | Relationship | Key Dependency |
| --- | --- | --- |
| ATLAS-MASTER-v1.2.docx | Parent Architecture | ATLAS product portfolio position, platform standards |
| ATLAS-ARCH.docx | Architecture Standards | Integration patterns, event bus contracts, API style |
| ATLAS-SEC.docx | Security Standards | Tenant isolation rules, audit logging standards, RBAC model |
| ATLAS-GOV.docx | Governance | Terminology, change control, ADR requirements |
| ATLAS-IMPL-PLATFORM.docx | Shared Services | Identity, Tenant, API Gateway, Notify — all consumed by Desk |
| ATLAS-IMPL-AI.docx | AI Platform | AI Gateway endpoints, RAG infrastructure, model catalog |
| ATLAS-IMPL-RESOLVE.docx | Related Product | Cross-product event boundary definition — external vs internal tickets |
| ATLAS-IMPL-PULSE.docx | Wave 3 Co-delivery | Shared sprint cadence, customer data cross-reference |
| ATLAS-IMPL-NEXUS.docx | Wave 3 Co-delivery | Asset/procurement data integration from ERP |
| atlas-desk-api.yaml | API Specification | Full OpenAPI 3.0 contract for all Desk endpoints |
| atlas-events-asyncapi.yaml | Event Contracts | Extend with desk.* events per ATLAS standards |
| ATLAS-DESK-PROMPTS-v1.0.md | AI Prompts Library | All structured prompts for Desk engineering team |
| CLAUDE.md | Claude Project Config | Project instructions and agent behaviors for Desk AI-assisted development |

--- End of AppLogica Desk Implementation Plan ---

AppLogica ATLAS — Desk (ITSM) Implementation Plan v1.0